## Tracking Log
VDOT Project: XYZ Project
Project:
CONTRACT ID #:
| CORR | Correspondence
| EMAIL | Email
| MEET | Meeting Minutes
| MEMO | Memo (Internal)
| MISC | Miscellaneous Files
Open
Closed
ID Number | Process | Description / Issue | Pay Package Reference | Date Received or Sent | From | To | Status (Open/ Closed | Record File Location Or Insert Hyperlink (ctrl + k)
C00011111DB00-1 | CORR | VDOT to Design-Builder - Notice of Intent Letter | n/a | 2007-05-09 | VDOT | Design-Builder | Closed
C00011111DB00-2 | CORR | Performance and Payment Bonds | n/a | 2007-05-11 | Design-Builder | AAA | Closed
C00011111DB00-3 | CORR | Certificate of Insurance | n/a | 2007-05-15 | Design-Builder | CCC | Closed
C00011111DB00-4 | CORR | SWPP Certification Permit | n/a | 2007-05-15 | Design-Builder | Design-Builder | Closed
C00011111DB00-5 | CORR | C112 - Binding Agreements | n/a | 2007-05-17 | Design-Builder | BBB | Closed
C00011111DB00-6 | CORR | VDOT Request for Design-Builder Preconstruction Meeting | n/a | 2007-06-09 | VDOT | Design-Builder | Closed
C00011111DB00-7 | CORR | Design-Builder to VDOT - Escrow Document Review Meeting | n/a | 2007-06-15 | Design-Builder | VDOT | Closed
C00011111DB00-8 | CORR | VDOT to Design-Builder - CTB Award | n/a | 2007-06-21 | VDOT | Design-Builder | Closed
C00011111DB00-9 | MISC | Design-Builder Questions Regarding Final Contract Document Timeline | n/a | 2007-06-22 | Design-Builder | VDOT | Closed
C00011111DB00-10 | CORR | Design-Builder to VDOT - Preconstruction Meeting | n/a | 2007-07-17 | Design-Builder | VDOT | Closed
C00011111DB00-11 | CORR | VDOT to Design-Builder - Final Contract Documents | n/a | 2007-07-18 | VDOT | Design-Builder | Closed
C00011111DB00-12 | MEET | Preconstruction Meeting Minutes | n/a | 2007-07-23 | Design-Builder | VDOT | Closed
C00011111DB00-13 | CORR | VDOT to Design-Builder - Notice to Proceed | n/a | 2007-08-02 | VDOT | Design-Builder | Closed
C00011111DB00-14 | CORR | Design-Builder to VDOT Permit Application Request | 1 | 2007-08-02 | Design-Builder | VDOT | Closed
C00011111DB00-15 | EMAIL | Geotechnical Investigations - Preliminary Data | 2 | 2007-08-08 | Design-Builder | Design-Builder | Closed
C00011111DB00-16 | CORR | Design-Builder to VDOT - Flood Plain Study Inquiry | 3 | 2007-08-09 | Design-Builder | VDOT | Closed
C00011111DB00-17 | CORR | Payment Requisition # 1 - First submission | 1,2,3 | 2007-08-10 | Design-Builder | VDOT | Closed
C00011111DB00-18 | CORR | Payment Requisition # 1 - Second submission | 1,2,3 | 2007-08-13 | Design-Builder | VDOT | Closed
C00011111DB00-19 | MEMO | VDOT Acknowledgement of Receipt of Preliminary Roadway Plans | 4 | 2007-08-14 | VDOT | Design-Builder | Closed
C00011111DB00-20 | MEMO | VDOT to Design-Builder - ROW Plan Submittal 1 Comments | 5 | 2007-08-22 | VDOT | Design-Builder | Closed
C00011111DB00-21 | CORR | VDOT ID Outstanding Issues to Design-Builder | 5 | 2007-08-24 | VDOT | Design-Builder | Closed
C00011111DB00-22 | CORR | VDOT to Design-Builder - Comments Regarding Preliminary Roadway Plans | 4 | 2007-09-05 | VDOT | Design-Builder | Closed
C00011111DB00-23 | CORR | Payment Requisition # 2 | 4,5 | 2007-09-10 | Design-Builder | VDOT | Closed
C00011111DB00-24 | MEMO | NVRPA Comments - Bridge Details | 6 | 2007-09-16 | NVRPA | Design-Builder | Closed
C00011111DB00-25 | CORR | Design-Builder to VDOT - Outstanding Issues | n/a | 2007-09-18 | Design-Builder | VDOT | Closed
C00011111DB00-26 | CORR | FWD: FOIA Request Mrs. Smith | n/a | 2007-09-20 | VDOT | Design-Builder | Closed
C00011111DB00-27 | CORR | FOIA Response to Mrs. Smith | n/a | 2007-09-23 | Design-Builder | VDOT | Closed
C00011111DB00-28 | MEMO | Memo to File - Reporting Requirements | n/a | 2007-09-25 | DDD | File | Closed
C00011111DB00-29 | CORR | Conflict of Interest Request for Determination | n/a | 2007-09-27 | OAG | VDOT | Closed
C00011111DB00-30 | CORR | VDOT Acknowledgement of Receipt of Final Roadway Plans | 7 | 2007-10-04 | VDOT | Design-Builder | Closed
C00011111DB00-31 | CORR | Payment Requisition # 3 | 6,7 | 2007-10-10 | Design-Builder | VDOT | Closed
C00011111DB00-32 | CORR | VDOT to Design-Builder - Comments Regarding Final Roadway Plans | 7 | 2007-10-17 | VDOT | Design-Builder | Closed
C00011111DB00-33 | MEET | Permit Coordination Meeting Minutes | 8 | 2007-10-26 | VDOT | Design-Builder | Closed
C00011111DB00-34 | CORR | Town of Leesburg Comment - Utililty Relocation Plans | 9 | 2007-10-27 | Design-Builder | VDOT | Open

## Instructions
Instructions for Use of the Log
General:
This tracking log is intended to track project-specific documents.
Filling Out the Form:
To add an item, use the next available ID Number,
Date Received' - Use date received by IPD. For outgoing correspondence, use correspondence date. If no date, electronic file, or fax use date stored in file name, top of fax, etc. Processes initiated on the last business day of the week shall be acknowledged before 5:00 PM on the next VDOT business day.
Insert Hyperlink:
Hold down the "Control" key and press "k", then browse for the file.